## Sheet1
Task Name | Duration | Start | Finish | Resource Names | Current Status | Remarks
Panorama Phase 2 | 153 days | Tue 12/1/15 | Thu 6/30/16
Planning and High Level Requirements | 44 days | Tue 12/1/15 | Fri 1/29/16
Prepare High level Scope Statement | 15 days | Tue 12/1/15 | Mon 12/21/15
Complete Wholesale Risk Management Plan | 2 days | Tue 12/22/15 | Wed 12/23/15
Finalize the Full Year Forecast in STAMP | 2 days | Thu 12/24/15 | Fri 12/25/15
Set Prelimanary Data Scope | 2 days | Mon 12/28/15 | Tue 12/29/15
Define High Level Requirements including Logical Data Model in Version One | 2 days | Wed 12/30/15 | Thu 12/31/15
Add Test Plan to all the version one stories | 1 day | Fri 1/1/16 | Fri 1/1/16
Story Jam | 1 day | Mon 1/4/16 | Mon 1/4/16
Finalize data release scope and approach | 1 day | Tue 1/5/16 | Tue 1/5/16
Complete Logical Architecture Model | 1 day | Wed 1/6/16 | Wed 1/6/16
Review Logical Architecture Model | 1 day | Thu 1/7/16 | Thu 1/7/16
Engage Enterprise Architecture for a Logical Design Architecture Project Review | 1 day | Fri 1/8/16 | Fri 1/8/16
Complete Functional Design Document(s) | 1 day | Mon 1/11/16 | Mon 1/11/16
Ensure Wholesale Project Architect Reviews FSD | 1 day | Tue 1/12/16 | Tue 1/12/16
Obtain Design Document Approvals | 1 day | Wed 1/13/16 | Wed 1/13/16
Complete the Test Strategy | 1 day | Thu 1/14/16 | Thu 1/14/16
Obtain Test Strategy Approval | 1 day | Fri 1/15/16 | Fri 1/15/16
Complete Implementation and Transition Strategy | 1 day | Mon 1/18/16 | Mon 1/18/16
Communicate Project Plan/Schedule to Stakeholders | 1 day | Tue 1/19/16 | Tue 1/19/16
Complete Requirements Traceability Through Design | 1 day | Wed 1/20/16 | Wed 1/20/16
Prepare Project Plan | 1 day | Thu 1/21/16 | Thu 1/21/16 | Ankur
Project Plan | 1 day | Fri 1/22/16 | Fri 1/22/16 | Ankur
BRD | 1 day | Mon 1/25/16 | Mon 1/25/16 | Ankur
FSD | 1 day | Tue 1/26/16 | Tue 1/26/16 | Ankur
Test Plan document | 1 day | Wed 1/27/16 | Wed 1/27/16 | Ankur
Test Script | 1 day | Thu 1/28/16 | Thu 1/28/16 | Ankur
Planning and High Level Requirements Complete | 1 day | Fri 1/29/16 | Fri 1/29/16 | Ankur
Data Modelling and Finalizing Data Flow | 14 days | Mon 2/1/16 | Thu 2/18/16
Data Modelling/Prepare Data Model Diagram | 5 days | Mon 2/1/16 | Fri 2/5/16
Finalizing Data Flow for different sources/Prepare Data Flow Diagrams | 3 days | Mon 2/8/16 | Wed 2/10/16
Walkthrough Data Model and Data Flow with Business/IT | 1 day | Thu 2/11/16 | Thu 2/11/16
Mapping Document | 3 days | Fri 2/12/16 | Tue 2/16/16
Data Model and Data Flow Diagrams | 1 day | Wed 2/17/16 | Wed 2/17/16
Data Modelling and Finalizing Data Flow Complete | 1 day | Thu 2/18/16 | Thu 2/18/16
Phase 1 Enhancements | 19 days | Mon 2/1/16 | Thu 2/25/16
Fix Phase 1 Enhancements/Defects | 12 days | Mon 2/1/16 | Tue 2/16/16 | Subhashree,Anitha,Sweta/Chiranjeevi
Migration of Phase 1 Enhancements to UAT Env | 2 days | Wed 2/17/16 | Thu 2/18/16 | Subhashree,Anitha,Sweta/Chiranjeevi
UAT Testing support of Phase 1 Enhancements | 5 days | Fri 2/19/16 | Thu 2/25/16 | Subhashree,Anitha,Sweta/Chiranjeevi
Panorama OBI Integration with RV2.0 (ETL) | 82 days | Fri 2/19/16 | Mon 6/13/16 |  |  | Expected date of Completion is 9th May as per Mukesh, but looking at the work can not be completed by 5/9
Requirement Analysis | 7 days | Fri 2/19/16 | Mon 2/29/16
Anlysis of User Stories,Data Model and Data Mapping Document - Ph2 | 5 days | Fri 2/19/16 | Thu 2/25/16
Review requirement Analysis - Ph 2 | 2 days | Fri 2/26/16 | Mon 2/29/16
Design | 12 days | Tue 3/1/16 | Wed 3/16/16
RV Snapshot to Staging | 10 days | Tue 3/1/16 | Mon 3/14/16
Staging to Star Schema - Phase2 | 10 days | Tue 3/1/16 | Mon 3/14/16
Review Design Document - Phase 2 | 1 day | Tue 3/15/16 | Tue 3/15/16
Sgn off Design Document - Phase 2 | 1 day | Wed 3/16/16 | Wed 3/16/16
Build - Datamodel and ETL | 23 days | Thu 3/17/16 | Mon 4/18/16
Package development for RV snapshot to Staging | 15 days | Thu 3/17/16 | Wed 4/6/16
Rework on packages developed for star schema | 15 days | Thu 3/17/16 | Wed 4/6/16
New package development for changes to Star schema | 15 days | Thu 3/17/16 | Wed 4/6/16
Master package creation for RV snapshot to Staging | 3 days | Thu 4/7/16 | Mon 4/11/16
Handshaking mechanism between RV snapshot and Staging | 3 days | Thu 4/7/16 | Mon 4/11/16
Handshaking mechanism between Staging and star Schema | 3 days | Thu 4/7/16 | Mon 4/11/16
End to end testing of Handshaking mechanism from RV snapshot to Star Schema | 2 days | Tue 4/12/16 | Wed 4/13/16
implement Email Notification for any failure | 3 days | Thu 4/14/16 | Mon 4/18/16
Unit Testing | 5 days | Thu 4/7/16 | Wed 4/13/16
Unit Testing and Unit Testing Document Prepartion | 5 days | Thu 4/7/16 | Wed 4/13/16
Capture Unit Test Result | 5 days | Thu 4/7/16 | Wed 4/13/16
SIT | 15 days | Thu 4/14/16 | Wed 5/4/16
SIT Deployment Plan | 1 day | Thu 4/14/16 | Thu 4/14/16
Prepare SIT Deployment Checklist | 1 day | Fri 4/15/16 | Fri 4/15/16
SIT Migration | 3 days | Mon 4/18/16 | Wed 4/20/16
SIT Support | 10 days | Thu 4/21/16 | Wed 5/4/16
UAT | 8 days | Thu 5/5/16 | Mon 5/16/16
UAT Deployment Plan | 1 day | Thu 5/5/16 | Thu 5/5/16
Prepare UAT Deployment Checklist | 1 day | Fri 5/6/16 | Fri 5/6/16
UAT Migration | 1 day | Mon 5/9/16 | Mon 5/9/16
UAT Support | 5 days | Tue 5/10/16 | Mon 5/16/16
Production Implementation | 20 days | Tue 5/17/16 | Mon 6/13/16
Sign Off for Production Implementation | 2 days | Tue 5/17/16 | Wed 5/18/16
Create CR for ETL and OBIEE deployment | 5 days | Thu 5/19/16 | Wed 5/25/16
Create Deployment Plan and Recovery Plan | 5 days | Thu 5/26/16 | Wed 6/1/16
Create Deployment and recovery plan for ETL jobs | 2 days | Thu 6/2/16 | Fri 6/3/16
Follow deployment plan for May release | 1 day | Mon 6/6/16 | Mon 6/6/16
May Production Rollout Complete | 1 day | Tue 6/7/16 | Tue 6/7/16
Post Production Fix | 1 day | Wed 6/8/16 | Wed 6/8/16
Monitor User Experience | 1 day | Thu 6/9/16 | Thu 6/9/16
Monitor ETL load, OBIEE performance and create baseline reports of performance metrics | 1 day | Fri 6/10/16 | Fri 6/10/16
Run adoption statistics | 1 day | Mon 6/13/16 | Mon 6/13/16
Post Implementation Support - during RV Data Conversions | 13 days | Tue 6/14/16 | Thu 6/30/16 |  |  | Reduced 2 days of effort to meet the 30th June timeline